RWJF GRANT TIMELINE & CALENDAR

Grant: GRT000937 | Total: $1,000,000 | Period: May 2025 – May 2027

| 📅 YEAR 1 May 15, 2025 – May 14, 2026 Budget: $448,029 ⚠️ REPORT DUE: ~May 2026 | 📅 YEAR 2 May 15, 2026 – May 14, 2027 Budget: $523,029 ⚠️ FINAL REPORT: ~May 2027 |
| --- | --- |

🎯 1. KEY MILESTONES BY AIM

| AIM | MILESTONE | TARGET DATE | BUDGET |
| --- | --- | --- | --- |
| 1 | DEI Dashboard Software acquired | Year 1 (by Dec 2025) | $50K Yr1, $25K Yr2 |
| 1 | Climate Survey deployed | Year 1 (Spring 2026) | Included above |
| 2 | Mini-Med School expanded to 10 schools | Ongoing | ~$8K supplies |
| 2 | Kid's Brain Club curriculum standardized | Year 1 | Included above |
| 3 | SEEDS Program (Summer) | August 9-13, 2026 | Aim 3 allocation |
| 3 | HUIPP Summer Program | Summer 2027 (Year 2) | $150K |
| 4 | Student Hardship Scholarships | Ongoing ($50K/yr) | $100K total |
| 4 | Research Equity Fund (Travel) | Ongoing | $25K Yr1, $50K Yr2 |
| 4 | Food Pantry stocked | Biweekly | $8K/yr |
| 5 | Faculty Re-Entry Grants awarded | Feb-Mar 2026 | 5 × $15K = $75K/yr |
| 5 | Faculty Retreat | Spring 2026 | ~$31-34K |

📆 2. CRITICAL DATES (Calendar Year 2026)

| DATE | EVENT / DEADLINE | ACTION REQUIRED |
| --- | --- | --- |
| Jan 2026 | Aim 5 Review Committee finalizing | Resolve COIs, assign reviewers |
| Feb 2026 | Faculty Re-Entry Grant reviews due | Compile scores, select winners |
| Feb 4 | OFD Planning Meeting | Next steps with MGL |
| Feb 12 | Dr. Goell's "Navigating Faculty Success" | e-Value blast (Veronica) |
| Mar 2026 | Award notifications sent | Letters to winners/non-awardees |
| Mar 27-29 | ACC Conference (Taylor Bell travel) | Ensure CBT booking complete |
| Spring 2026 | Faculty Retreat @ Gallaudet | Finalize venue, breakout rooms |
| May 2026 | ⚠️ YEAR 1 REPORT DUE TO RWJF | Compile metrics, spending report |
| Aug 9-13 | SEEDS Program | Hotel quotes, participant coordination |
| Summer 2027 | HUIPP Program (Year 2) | $150K for housing/stipends |

💰 3. BUDGET SPENDING PACE (Year 1)

Year 1 Budget: $448,029 | Monthly Target: ~$37,336/month

| CATEGORY | YEAR 1 BUDGET | MONTHLY PACE | NOTES |
| --- | --- | --- | --- |
| Personnel + Fringe | $141,029 | $11,752 | Fixed cost (salary + benefits) |
| Supplies | $110,000 | $9,167 | Software, dashboard, materials |
| Travel | $30,000 | $2,500 | Student + PI/Director travel |
| Food | $10,000 | $833 | Food Pantry + faculty spaces |
| Participant Support | $100,000 | $8,333 | Stipends $50K, Travel $25K, Tuition $25K |
| Subcontracts (Faculty) | $57,000 | $4,750 | Microgrants + Re-Entry Grants |

📊 4. RWJF REPORTING REQUIREMENTS

⚠️ YEAR 1 PROGRESS REPORT (Due ~May 2026) Prepare to report on: • Aim 1: DEI Dashboard status, Climate Survey results, policy reforms • Aim 2: # of Title I schools reached, Mini-Med School metrics • Aim 3: SEEDS program preparation status • Aim 4: # students supported (hardship, travel), Food Pantry utilization • Aim 5: # Faculty Re-Entry Grants awarded, workshop attendance • Financial: Budget vs. Actual spending by category Contact: Sheryl Robertson (RWJF Comms Officer)

🔢 5. QUICK REFERENCE: KEY NUMBERS

| 📊 BUDGET TOTALS Total Award: $971,058 Year 1: $448,029 Year 2: $523,029 Participant Support: $350,000 | 🎯 KEY DELIVERABLES Faculty Re-Entry Grants: 5/year Student Travel Slots: 15/year Hardship Students: 20/year max HUIPP Students: 24 (Summer 2027) |
| --- | --- |

Grant: GRT000937 | PI: Dr. Marjorie Gondré-Lewis | Prepared by: Héctor Bravo-Rivera, PhD | Print and post